## GANTT_draft
Gantt chart |  |  | WrasseFEED
Activity Description | Leader | Partners | Month Start | Month End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
WP1: Research on feeds for ballan wrasse | SPAROS |  | 1 | 8 | [24 empty] | WP1: Research on feeds for ballan wrasse - [M1 - M8]; | bar: 1 to 24
T1.1 Nutritional requirements for larvae and juveniles of ballan wrasse | SPAROS |  | 1 | 8 | [24 empty] | T1.1 Nutritional requirements for larvae and juveniles of ballan wrasse - [M1 - M8]; | bar: 1 to 8
T1.2 Identification of functional ingredients / additives of interest | SPAROS |  | 1 | 8 | [24 empty] | T1.2 Identification of functional ingredients / additives of interest - [M1 - M8]; | bar: 1 to 8
T1.3 Research on weaning microdiets for ballan wrasse | SPAROS |  | 1 | 8 | [24 empty] | T1.3 Research on weaning microdiets for ballan wrasse - [M1 - M8]; | bar: 1 to 8
T1.4 Research on soft-textured feeds for nursery and ongrowing stages of ballan wrasse | SPAROS |  | 1 | 8 | [24 empty] | T1.4 Research on soft-textured feeds for nursery and ongrowing stages of ballan wrasse - [M1 - M8]; | bar: 1 to 8
WP2: Lab-scale efficacy trials of feeds | OTTER FERRY |  | 1 | 18 | [24 empty] | WP2: Lab-scale efficacy trials of feeds - [M1 - M18]; | bar: 1 to 18
T2.1 Trials with weaning microdiets for ballan wrasse | OTTER FERRY | SPAROS | [26 empty] | T2.1 Trials with weaning microdiets for ballan wrasse - [M - M];
T2.2 Trials with grow-out feeds for nursery and ongrowing stages of ballan wrasse | OTTER FERRY | SPAROS | [26 empty] | T2.2 Trials with grow-out feeds for nursery and ongrowing stages of ballan wrasse - [M - M];
T2.3 Trials with functional feeds for nursery and ongrowing stages of ballan wrasse | OTTER FERRY | SPAROS | [26 empty] | T2.3 Trials with functional feeds for nursery and ongrowing stages of ballan wrasse - [M - M];
T2.4 Evaluation of diet effect on gut microbiota of ballan wrasse | OTTER FERRY | SPAROS + U. Plymouth ? | [26 empty] | T2.4 Evaluation of diet effect on gut microbiota of ballan wrasse - [M - M];
T2.5 Evaluation of diet effect on immune and anti-oxidant systems of ballan wrasse | SPAROS | CIIMAR? | [26 empty] | T2.5 Evaluation of diet effect on immune and anti-oxidant systems of ballan wrasse - [M - M];
WP3: Commercial-scale validation of feeds | OTTER FERRY |  | 18 | 24 | [24 empty] | WP3: Commercial-scale validation of feeds - [M18 - M24]; | bar: 18 to 24
T3.1 Trials with weaning microdiets for ballan wrasse | OTTER FERRY | SPAROS | [26 empty] | T3.1 Trials with weaning microdiets for ballan wrasse - [M - M];
T3.2 Trials with grow-out feeds for nursery and ongrowing stages of ballan wrasse | OTTER FERRY | SPAROS | [26 empty] | T3.2 Trials with grow-out feeds for nursery and ongrowing stages of ballan wrasse - [M - M];
T3.3 Trials with functional feeds for nursery and ongrowing stages of ballan wrasse | OTTER FERRY | SPAROS | [26 empty] | T3.3 Trials with functional feeds for nursery and ongrowing stages of ballan wrasse - [M - M];
WP4: Dissemination and Exploitation | SPAROS |  | 18 | 24 | [24 empty] | WP4: Dissemination and Exploitation - [M18 - M24]; | bar: 1 to 24
T4.1 Market analyses and monitoring | SPAROS | OTTER FERRY | 1 | 24 | [24 empty] | T4.1 Market analyses and monitoring - [M1 - M24]; | bar: 1 to 24
T4.2 Dissemination | SPAROS | OTTER FERRY | 14 | 24 | [24 empty] | T4.2 Dissemination - [M14 - M24]; | bar: 14 to 24
WP5: Project Management | SPAROS |  | 1 | 24 | [24 empty] | WP5: Project Management - [M1 - M24]; | bar: 1 to 24
T5.1 Project Management | SPAROS | OTTER FERRY | 1 | 24 | [24 empty] | T5.1 Project Management - [M1 - M24]; | bar: 1 to 24

## GANTT based on WP list
GANTT Chart |  |  | Proposal Title
Activity Description | Leader | Partners | Month Start | Month End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | Del | Lead | Due month | Description | MS | Description | Due month | WP - Tasks | Question für Proposal Development
WP1: Descriptive and catching title 1 | Name | Partner1, Partner 2 - X | 1 | 18 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | WP1: Descriptive and catching title 1 - [M1 - M18];
T1.1 |  |  | 1 | 18 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | T1.1 - [M1 - M18];
T1.2 |  |  | 1 | 12 | X | X | X | X | X | X | X | X | X | X | X | X | [43 empty] | T1.2 - [M1 - M12];
T1.3 |  |  | 6 | 12 | [5 empty] | X | X | X | X | X | X | X | [43 empty] | T1.3 - [M6 - M12];
T1.4 |  |  | 6 | 18 | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | T1.4 - [M6 - M18];
WP2: Descriptive and catching title 2 |  |  | 6 | 48 | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP2: Descriptive and catching title 2 - [M6 - M48];
T2.1 |  |  | 12 | 48 | [11 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T2.1 - [M12 - M48];
T2.2 |  |  | 6 | 30 | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [25 empty] | T2.2 - [M6 - M30];
T2.3 |  |  | 12 | 48 | [11 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T2.3 - [M12 - M48];
T2.4 |  |  | 16 | 48 | [15 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T2.4 - [M16 - M48];
WP3: Descriptive and catching title 3 |  |  | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP3: Descriptive and catching title 3 - [M19 - M48];
T3.1 |  |  | 36 | 48 | [35 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T3.1 - [M36 - M48];
T3.2 |  |  | 19 | 31 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [24 empty] | T3.2 - [M19 - M31];
T3.3 |  |  | 32 | 48 | [31 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T3.3 - [M32 - M48];
T3.4 |  |  | 32 | 48 | [31 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T3.4 - [M32 - M48];
WP4: Descriptive and catching title 4 |  |  | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP4: Descriptive and catching title 4 - [M19 - M48];
T4.1 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T4.1 - [M19 - M36];
T4.2 |  |  | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T4.2 - [M19 - M48];
T4.3 |  |  | 24 | 48 | [23 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T4.3 - [M24 - M48];
T4.4 |  |  | 36 | 48 | [35 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T4.4 - [M36 - M48];
WP5: Descriptive and catching title 5 |  |  | 12 | 48 | [11 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP5: Descriptive and catching title 5 - [M12 - M48];
T5.1 |  |  | 12 | 19 | [11 empty] | X | X | X | X | X | X | X | X | [36 empty] | T5.1 - [M12 - M19];
T5.2 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T5.2 - [M19 - M36];
T5.3 |  |  | 24 | 36 | [23 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T5.3 - [M24 - M36];
T5.4 |  |  | 30 | 46 | [29 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [9 empty] | T5.4 - [M30 - M46];
WP6: Descriptive and catching title 6 |  |  | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP6: Descriptive and catching title 6 - [M19 - M48];
T6.1 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T6.1 - [M19 - M36];
T6.2 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T6.2 - [M19 - M36];
T6.3 |  |  | 24 | 32 | [23 empty] | X | X | X | X | X | X | X | X | X | [23 empty] | T6.3 - [M24 - M32];
T6.4 |  |  | 36 | 48 | [35 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T6.4 - [M36 - M48];
WP7: Dissemination and Communication Strategy |  |  | 1 | 18 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | WP7: Dissemination and Communication Strategy - [M1 - M18];
T7.1 DEC Plan |  | all partners | 1 | 6 | X | X | X | X | X | X | [42 empty] | D7.1 |  | 5 | DEC Plan |  |  |  | T7.1 DEC Plan - [M1 - M6];
T7.2 Tailored Stakeholder Integration |  |  | 6 | 12 | [5 empty] | X | X | X | X | X | X | X | [43 empty] | T7.2 Tailored Stakeholder Integration - [M6 - M12];
T7.3 MAA/ Targeted liaison activities for strategic networking |  | all partners | 6 | 18 | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | T7.3 MAA/ Targeted liaison activities for strategic networking - [M6 - M18];
T7.4 MAA-reinforced Capacity Building Concept |  |  | 19 | 24 | [18 empty] | X | X | X | X | X | X | [24 empty] | D7.4 |  | 24 | Capacity Building Concept |  |  |  | T7.4 MAA-reinforced Capacity Building Concept - [M19 - M24];
WP8: Tailored Outreach, Exploitation and Support | [59 empty] | WP8: Tailored Outreach, Exploitation and Support - [M - M ];
T 8.1 Monitor, evaluate, and enhance outreach impact |  | all partners | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T 8.1 Monitor, evaluate, and enhance outreach impact - [M19 - M48];
T.8.2 Synergistic activities with European (and other international) projects |  | all partners | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T.8.2 Synergistic activities with European (and other international) projects - [M19 - M48];
T8.3 Implementing exploitation pathways and IPR management |  | all partners | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T8.3 Implementing exploitation pathways and IPR management - [M19 - M48];
T8.4 Inform/ Support Agenda Setting for the relevant EU policies |  |  | 36 | 48 | [35 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T8.4 Inform/ Support Agenda Setting for the relevant EU policies - [M36 - M48];
WP9: Descriptive and catchy title 9 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | WP9: Descriptive and catchy title 9 - [M19 - M36];
T9.1 |  |  | 19 | 24 | [18 empty] | X | X | X | X | X | X | [31 empty] | T9.1 - [M19 - M24];
T9.2 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T9.2 - [M19 - M36];
T9.3 |  |  | 24 | 36 | [23 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T9.3 - [M24 - M36];
WP10: Descriptive and catchy title 10 |  |  | 37 | 48 | [36 empty] | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP10: Descriptive and catchy title 10 - [M37 - M48];
T10.1 |  |  | 37 | 48 | [36 empty] | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T10.1 - [M37 - M48];
T10.2 |  |  | 37 | 46 | [36 empty] | X | X | X | X | X | X | X | X | X | X | [9 empty] | T10.2 - [M37 - M46];
T10.3 |  |  | 44 | 48 | [43 empty] | X | X | X | X | X | [7 empty] | T10.3 - [M44 - M48];
WP11: Descriptive and catchy title 11 |  |  | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP11: Descriptive and catchy title 11 - [M19 - M48];
T11.1 |  |  | 19 | 36 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T11.1 - [M19 - M36];
T11.2 |  |  | 24 | 36 | [23 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [19 empty] | T11.2 - [M24 - M36];
T11.3 |  |  | 24 | 48 | [23 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T11.3 - [M24 - M48];
T11.4 |  |  | 37 | 48 | [36 empty] | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T11.4 - [M37 - M48];
WP12: Project and Data Management | Coordinator |  | 1 | 18 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | WP12: Project and Data Management - [M1 - M18];
T12.1 Strategic, technical, administrative and financial management |  |  | 1 | 18 | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | T12.1 Strategic, technical, administrative and financial management - [M1 - M18];
T12.2 Data management and open science |  |  | 3 | 18 |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [30 empty] | 12.1 | DIL | 3 | Data Management Plan |  |  |  | T12.2 Data management and open science - [M3 - M18];
T12.3 Operationalise Quality Monitoring, & Risk Management |  |  | 6 | 18 | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [37 empty] | T12.3 Operationalise Quality Monitoring, & Risk Management - [M6 - M18];
WP13: Coordination, Ethics and Legacy | Coordinator |  | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | WP13: Coordination, Ethics and Legacy - [M19 - M48];
T13.1 Check and optimise effectiveness of performance monitoring, and quality assurance protocols for project management |  | all partners | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T13.1 Check and optimise effectiveness of performance monitoring, and quality assurance protocols for project management - [M19 - M48];
T13.2 Ethics management and Responsible Research and Innovation (RRI) |  | all partners | 19 | 48 | [18 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T13.2 Ethics management and Responsible Research and Innovation (RRI) - [M19 - M48];
T13.3 Project legacy planning |  | all partners | 36 | 48 | [35 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | [7 empty] | T13.3 Project legacy planning - [M36 - M48];
Consortium meetings |  |  |  |  | 1 | [10 empty] | 2 | [11 empty] | 3 | [11 empty] | 4 | [11 empty] | 5 | [7 empty] | Consortium meetings - [M - M];
[5 empty] | UHOH | [10 empty] | Name Host | [11 empty] | Name Host | [11 empty] | Name Host | [11 empty] | Brussels?